## Project Plan Template
Phase/Milestone/Task | Responsible Parties
INITIATION:
Sales-to-PM Hand Off Meeting | Project Manager
Create Project Charter | Project Manager
PLANNING:
Project Kick Off w/ Customer | Customer, Project Manager
Project Plan Baseline Build | Project Manager
Project Resource(s) Coordination | Project Manager
Finalize Team Members | Project Manager
Internal Kick-Off Call with Project Team | Project Manager, Implementation Technician, Application Engineer, System Engineer, Integration Specialist, Consultant, Clinical Educator
On-Site Credentialing Requirements (Resource #1) | System Engineer
On-Site Credentialing Requirements (Resource #2) | Implementation Technician
On-Site Credentialing Requirements (Resource #3) | Clinical Educator
EXECUTION:
Technical Requirements Preparation | Project Manager
Create Server Architecture Diagram | Integration Specialist
Create Site Info Document | Integration Specialist
Review wiring with Cabling Vendor (Call) | Project Manager
Review BLE Tag Pre-requisites | Project Manager, Application Engineer, System Engineer, Integration Specialist
Review RT App Pre-requisites | Project Manager, Application Engineer, System Engineer, Integration Specialist
Initial Design (RTLS Core)🔹 | System Engineer
Initial Design (Wayfinding)🔹 | System Engineer
Initial Design (HH) | System Engineer
Initial Design (EM) | System Engineer
Initial Design (SS) | System Engineer
Software Installation (Connect) | Project Manager
Software Install (RTLS Core)🔹 | System Engineer
Setup Connect Pulse (New Sites only) | System Engineer
Software Installation (Asset)🔹 | Application Engineer
Software Installation (OnDemandOrder)🔹 | Application Engineer
Software Installation (EM)🔹 | Application Engineer
Software Installation (Clinical Workflow) 🔹 | Application Engineer
Software Installation (Staff Duress)🔹 | Application Engineer
Software Installation (HH/HHRT)🔹 | Application Engineer
Software Installation Core Connector (HHRT Only) | Application Engineer, System Engineer, Integration Specialist
Software Installation HHRT Services (Rabbit, CenTrak RTLS and SHIM) | Application Engineer, System Engineer, Integration Specialist
Software Installation (SS)🔹 | Application Engineer
Site Survey/Workshop Scheduling & Logistics | Project Manager
Solution Workshop (Asset)🔹 | Clinical Educator
Solution Workshop (Staff Duress)🔹 | Clinical Educator
Solution Workshop (Clinical Workflow) | Clinical Educator
Site Survey (RTLS Core)🔹 | Project Manager
On-Site Survey (RTLS Core) | Implementation Technician, System Engineer
Post Survey Documentation (RTLS Core) | Implementation Technician, System Engineer
Upload to Sharepoint (RTLS Core) | Implementation Technician, System Engineer
Survey Documents Approval (RTLS Core) | Project Manager
Solution Workshop (HH)🔹 | Clinical Educator
Site Survey (HH)🔹 | Project Manager
On-Site Survey (HH) | Implementation Technician, System Engineer
Post Survey Documentation (HH) | Implementation Technician, System Engineer
Upload to Sharepoint (HH) | Implementation Technician, System Engineer
Survey Documents Approval (HH) | Project Manager
Solution Workshop (EM)🔹 | Clinical Educator
Site Survey (EM) | Project Manager
On-Site Survey (EM) | Implementation Technician, System Engineer
Post Survey Documentation (EM) | Implementation Technician, System Engineer
Upload to Sharepoint (EM) | Implementation Technician, System Engineer
Survey Documents Approval (EM) | Project Manager
Solution Workshop (SS)🔹 | Clinical Educator
Site Survey (SS)🔹 | Project Manager
On-Site Survey (SS) | Implementation Technician, System Engineer
Post Survey Documentation (SS) | Implementation Technician, System Engineer
Upload to Sharepoint (SS) | Implementation Technician, System Engineer
Survey Documents Approval (SS) | Project Manager
Site Survey - Design and Reports Review | Project Manager
Solution Workshop (Wayfinding) | Clinical Educator
Final Design (RTLS Core)🔹 | Project Manager
Finalize Design for Install (RTLS Core) | System Engineer
Create Spacefile (RTLS Core) | System Engineer
Upload to Sharepoint (RTLS Core) | System Engineer
Final Design (HH)🔹 | Project Manager
Finalize Design for Install (HH) | System Engineer
Create Spacefile (HH) | System Engineer
Upload to Sharepoint (HH) | System Engineer
Final Design (SS)🔹 | Project Manager
Finalize Design for Install (SS) | System Engineer
Create Spacefile (SS) | System Engineer
Upload to Sharepoint (SS) | System Engineer
Final Design (Wayfinding) | System Engineer
📦 Hardware Shipment | Project Manager
📦 INI Training File (RTLS Core) | System Engineer
📦 INI Training File (SS) | System Engineer
📦 Delivery Date Confirmation w/ Customer | Project Manager
📦 HW Release - Tags & Badges | Project Manager
📦 HW Release - Infrastructure & Sensors | Project Manager
Software Install & Set Up (Wayfinding)🔹 | System Engineer
Map Configuration (Wayfinding)🔹 | Application Engineer, System Engineer
Solution Design & Change Order Sign-Off | Project Manager
Installation Pre-Deployment | Project Manager
Installation Logistics | Project Manager
Physical Installation (RTLS Core)🔹 | Project Manager
Install Hardware (RTLS Core) | Implementation Technician
Upload Spacefile to Sharepoint (RTLS Core) | Implementation Technician
Physical Installation (EM)🔹 | Project Manager
Install Hardware (EM) | Implementation Technician
Upload Workbook to Sharepoint (EM) | Implementation Technician
Physical Installation (Clinical Workflow)🔹 | Project Manager
Install Hardware (Clinical Workflow) | Implementation Technician
Upload Spacefile to Sharepoint (Clinical Workflow) | Implementation Technician
Physical Installation (HH)🔹 | Project Manager
Install Hardware (HH) | Implementation Technician
Upload Spacefile to Sharepoint (HH) | Implementation Technician
Physical Installation (SS)🔹 | Project Manager
Install Hardware (SS) | Implementation Technician
Upload Spacefile to Sharepoint (SS) | Implementation Technician
Physical Installation (Wayfinding)🔹 | Project Manager
Install Hardware (Wayfinding) | Implementation Technician
Upload Spacefile to Sharepoint (Wayfinding) | Implementation Technician
Software Configuration (RTLS Core)🔹 | Project Manager
HW Configuration w/in Core (RTLS) | System Engineer
Integration Development (RTLS) | System Engineer, Integration Specialist
Software Configuration (Asset/AssetRT)🔹 | Project Manager
UI Map Approval (Asset/AssetRT) | Application Engineer
UI Map Design (Asset/AssetRT)🔹 | Application Engineer
HW Configuration w/in UI (Asset/AssetRT) | Application Engineer
Integration Development (Asset/AssetRT) | Application Engineer, System Engineer, Integration Specialist
Software Configuration (Staff Duress/DuressRT)🔹 | Project Manager
UI Map Approval (Staff Duress/DuressRT) | Application Engineer
UI Map Design (Staff Duress/DuressRT)🔹 | Application Engineer
HW Configuration w/in UI (Staff Duress/DuressRT) | Application Engineer
Integration Development (Staff Duress/ DuressRT) | Application Engineer, System Engineer, Integration Specialist
DuressRT Alert Manager Install and Config (DuressRT) | Application Engineer, System Engineer, Integration Specialist
Software Configuration (EM)🔹 | Project Manager
HW Configuration w/in Core (EM) | Application Engineer, System Engineer
HW Configuration w/in UI (EM) | Application Engineer, System Engineer
Integration Development (EM) | Application Engineer, System Engineer, Integration Specialist
Software Configuration (HH/HHRT)🔹 | Project Manager
HW Configuration w/in Core (HH/HHRT) | Application Engineer, System Engineer
UI Map Approval (HH/HHRT) | Project Manager
UI Map Design (HH/HHRT) | Application Engineer, System Engineer
HW Configuration w/in UI (HH/HHRT) | Application Engineer, System Engineer
Integration Development (HH/HHRT) | Application Engineer, System Engineer, Integration Specialist
Software Configuration (SS)🔹 | Project Manager
HW Configuration w/in Core (SS) | Application Engineer, System Engineer
UI Map Approval | Project Manager
UI Map Design (SS)🔹 | Application Engineer, System Engineer
HW Configuration w/in UI (SS) | Application Engineer, System Engineer
Workstation Software Installation (SS)🔹 | Application Engineer, System Engineer
Integration Development (SS) | Application Engineer, System Engineer, Integration Specialist
Software Configuration (Clinical Workflow)🔹 | Project Manager
HW Configuration w/in Core (Clinical Workflow) | Application Engineer, System Engineer
HW & SW Configuration w/in UI (Clinical Workflow) | Application Engineer, System Engineer
Integration Development (Clinical Workflow) | Application Engineer, System Engineer, Integration Specialist
Certification Logistics | Project Manager
System Validation (RTLS) | Project Manager
Onsite System Testing & Certification (RTLS)🔹 | System Engineer
As-Built Documentation (RTLS) | System Engineer
Solution Validation (Asset/AssetRT)🔹 | Application Engineer
Solution Validation (Staff Duress/DuressRT)🔹 | Application Engineer
Upload Documentation in Sharepoint (RTLS) | System Engineer
System Validation (EM) | Project Manager
Testing & Certification (EM) | Application Engineer, System Engineer
Solution Validation (EM)🔹 | Application Engineer
Upload Documentation in Sharepoint (EM) | System Engineer
System Validation (Clinical Workflow) | Project Manager
As-Built Documentation (Clinical Workflow) | System Engineer
Solution Validation (Clinical Workflow) | Application Engineer
Upload Documentation in Sharepoint (Workflow) | System Engineer
System Validation (HH/HHRT) | Project Manager
Testing & Certification (HH)🔹 | System Engineer
As-Built Documentation (HH) | System Engineer
Upload Documentation in Sharepoint (HH) | System Engineer
System Validation (SS) | Project Manager
🔹 Testing & Certification (SS) | System Engineer
As-Built Documentation (SS) | System Engineer
Upload Documentation in Sharepoint (SS) | System Engineer
System Validation (Wayfinding) | Project Manager
Testing & Certification (Wayfinding)🔹 | Implementation Technician
As-Built Documentation (Wayfinding) | System Engineer
Upload Documentation in Sharepoint (Wayfinding) | System Engineer
Asset Tag Deployment (Asset)🔹 | Customer, Project Manager
Staff Badge Deployment (Clinical Workflow)🔹 | Customer, Project Manager
Staff Badge Deployment (Staff Duress)🔹 | Customer, Project Manager
Staff Badge Deployment (HH)🔹 | Customer, Project Manager
Solution Training (Asset/AssetRT) | Project Manager
End-User Training (Asset/AssetRT) | Application Engineer
Admin Training (Asset/AssetRT) | Application Engineer
Solution Training (EM) | Project Manager
End-User Training (EM) | Application Engineer
Admin Training (EM) | Application Engineer
Solution Training (Clinical Workflow) | Project Manager
End-User Training (Clinical Workflow) | Clinical Educator
Admin Training (Clinical Workflow) | Clinical Educator
Solution Training (Staff Duress/DuressRT) | Project Manager
End-User Training (Staff Duress/DuressRT) | Application Engineer
Admin Training (Staff Duress/DuressRT) | Application Engineer
Solution Training (SS) | Project Manager
🔹 End-User Training (SS) | Clinical Educator
🔹 Admin User Training (SS) | Clinical Educator
Solution Training (Wayfinding) | Project Manager
Admin Training (Wayfinding) | Application Engineer
User Acceptance Testing (UAT) | Project Manager
Schedule UAT with Customer | Project Manager
Finalize Test Cases with Customer | Project Manager
Conduct UAT | Application Engineer, System Engineer, Integration Specialist
Obtain UAT Signoff | Project Manager
Software Configuration (Cisco Spaces)🔹 | Project Manager
Cisco Spaces Connector Configuration | System Engineer
Wi-Fi and BLE UI Mapping (Activate) | System Engineer, Integration Specialist
Add CenTrak Distro Email Address on Cisco Spaces | Application Engineer, System Engineer, Integration Specialist, Project Manager
Software Installation (Connect Platform) | Project Manager
Create Customer in Connect Platform | Application Engineer, System Engineer, Integration Specialist
Configure AD in Connect Platform | Application Engineer, System Engineer, Integration Specialist
Solution Workshop (HHC)🔹 | Clinical Educator
Solution Workshop (EM) | Clinical Educator
Solution Training (HHC/HHCRT) | Project Manager
End-User Training (Asset/AssetRT) | Clinical Educator
Admin Training (Asset/AssetRT) | Clinical Educator
GO-LIVE:
Go-Live (Asset/AssetRT) | Project Manager
Soft Go-Live (Asset/AssetRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go/No-Go Decision (Asset/AssetRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Hard Go-Live (Asset/AssetRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go-Live (EM) | Project Manager
Soft Go-Live (EM) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go/No-Go Decision (EM) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Hard Go-Live (EM) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go-Live (Clinical Workflow) | Project Manager
Soft Go-Live (Clinical Workflow) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go/No-Go Decision (Clinical Workflow) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Hard Go-Live (Clinical Workflow) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go-Live (Staff Duress/DuressRT) | Project Manager
Soft Go-Live (Staff Duress/DuressRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go/No-Go Decision (Staff Duress/DuressRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
🔹 Hard Go-Live (Staff Duress/DuressRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go-Live (SS) | Project Manager
Internal Support Transition Call | Application Engineer, System Engineer, Integration Specialist, Project Manager
🔹 Go-Live Support (SS) | Application Engineer, System Engineer, Clinical Educator
Certified Workflow Documentation (SS) | Clinical Educator
Go-Live (HH/HHRT) | Project Manager
Soft Go-Live (HH/HHRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
Go/No-Go Decision (HH/HHRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
HH Baseline Data Collection | Customer, Clinical Educator
HH Baseline Data Review | Customer, Clinical Educator
🔹 Hard Go-Live (HH/HHRT) | Application Engineer, System Engineer, Integration Specialist, Project Manager
🔹 Role Level Consulting | Project Manager
Role Consulting Site Visit | Clinical Educator
🔹 Admin User Training (HH) | Clinical Educator
Call #1: Role Consulting | Clinical Educator
Call #2: Role Consulting | Clinical Educator
🔹 Unit Level Consulting | Project Manager
Unit Consulting Site Visit | Clinical Educator
Call #1: Unit Consulting | Clinical Educator
Call #2: Unit Consulting | Clinical Educator
🔹 Individual Level Consulting | Project Manager
Call #1: Individual Consulting | Clinical Educator
Call #2: Individual Consulting | Clinical Educator
Call #3: Individual Consulting | Clinical Educator
Certified Workflow Documentation (HH/HHRT) | Clinical Educator
Go-Live (Wayfinding) | Project Manager
Soft Go-Live (Wayfinding) | Project Manager, Application Engineer
Go/No-Go Decision (Wayfinding) | Project Manager, Application Engineer
Hard Go-Live (Wayfinding) | Project Manager, Application Engineer
Go-Live (Nurse Call) | Project Manager
RTLS Data Stream Enabled (Nurse Call) | System Engineer
As-Buil Documents Shared (Nurse Call) | System Engineer
Hard Go-Live (Nurse Call) | System Engineer
POST GO-LIVE TRANSITION:
(Internal) Support Handoff Call | Project Manager, Implementation Technician, Application Engineer, System Engineer, Integration Specialist, Consultant, Clinical Educator
(External) Support Handoff Call | Customer, Project Manager, Support
CLOSURE:
Project Close-Out Assessment | Project Manager
Net Promoter Score (CenTrak Service Operations) | Customer, Project Manager
Project Closed (Complete) | Customer, Project Manager